# Mission Proposal

ACE-MP-011

AUTHOR  Alex Morgan (fictional)     REVIEW  Instructor demonstration     STATUS  Proposed; awaits Mission Command review

# Purpose and assessment context

A structured instructor-authored model for CIT-205. It illustrates how technical work becomes verifiable evidence. All incidents, measurements, approvals and names below are fabricated for teaching.

## Mission

Standardize workstation readiness validation within a fictional instructional service desk.

## Problem

Inconsistent handoffs mean technicians cannot prove an endpoint meets the same baseline; work may be duplicated.

## Outcome

A versioned checklist, validation record template, escalation rules, and a reviewer acceptance checklist.

## Stakeholders

CIT-205 learners, instructor/reviewer, future support technicians. No real production authorization is asserted.

## Method

Research existing baselines, draft checklist, pilot three training devices using two independent reviewers, record disagreements, revise, seek approval.

## Acceptance

Two technicians independently obtain matching pass/flag decisions for three training devices; artifacts include evidence and privacy checks.

## Dependencies

Training asset access, approved baseline, review time. Risks: oversharing credentials, unauthorized changes, inconsistent scoring.

## Mitigation

Sanitization requirements, sign-off before changes, explicit expected vs actual, and peer-review checkpoint.

# Evidence and verification matrix

| DELIVERABLE | MEASURE | OWNER | STATE |
| --- | --- | --- | --- |
| Validation checklist | Peer-reviewed revision | Alex Morgan | Proposed |
| Three-device pilot | Matching outcomes | Two technicians | Not started |
| KB cross-reference | Working links | Documentation review | Planned |

# Reviewer handoff and quality assurance

Document: ACE-MP-011 | Revision: 1.2 | Classification: public instructional example

# Acceptance checklist

☐ Relevant user / system impact is defined without publishing confidential information.

☐ Expected outcomes are distinguished from the technician's actual observations.

☐ Every conclusion is supported by a specific test or appropriate evidence reference.

☐ Changes are authorized, reversible when appropriate, and documented.

☐ Closure includes verification, remaining risk, escalation, and reviewer disposition.

☐ Accessible language is used; screenshots and supporting files are safe for public release.

# Evidence register (model references)

ACE-MP-011 E-01 | Initial report or baseline. Synthetic exhibit reference, supplied to model documentation. Students replace with genuine, redacted records.

ACE-MP-011 E-02 | Troubleshooting observations. Synthetic exhibit reference, supplied to model documentation. Students replace with genuine, redacted records.

ACE-MP-011 E-03 | Change / review / authorization notes. Synthetic exhibit reference, supplied to model documentation. Students replace with genuine, redacted records.

ACE-MP-011 E-04 | Final validation and user confirmation. Synthetic exhibit reference, supplied to model documentation. Students replace with genuine, redacted records.

# Instructor review

What works: the record captures context, action, evidence and outcome. Before qualifying real student work, reviewers must inspect supporting artifacts and verify that any technical claim or metric is true.

Fictional review disposition: EXEMPLAR APPROVED FOR TEACHING ONLY.

# Reflection and next action

The value of this artifact is not the final checkbox; it is the trace from an observed symptom through a defensible decision to validated results. A real student should explain one revision made after feedback and link the relevant commit.